## Sheet1
| PROJECT | DOCUMENT SERVER
| GUIDE NAME: | DR. LN PADHI
| CO-GUIDE NAME: | MR. SUBHASHIS MISHRA
SL NO. | NAME | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
|  | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04
1 | AKSHAY KUMAR | 2021-12-02: Environment Setup; 2021-12-03: User Module (Registration); 2021-12-04: DataBase Module (Connectivity)
2 | KHUSHI | 2021-12-02: Environment Setup; 2021-12-03: Documentation (PHP); 2021-12-04: Documentation (PHP)
3 | NEHA BHAGAT | 2021-12-02: Environment Setup; 2021-12-03: Documentation (PHP); 2021-12-04: Content Page
4 | NIRANJAN SINGH | 2021-12-02: Environment Setup; 2021-12-03: User Module (Registration); 2021-12-04: DataBase Module (Connectivity)
SL NO. | NAME | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
|  | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11
1 | AKSHAY KUMAR | Admin Module (Registration) | Admin Module (Registration) | User Module (Logiin) | Database Module (User & Admin Validation ) | On Leave | Exam leave
2 | KHUSHI | Admin Module (Registration) | Admin Module (Registration) | User Module (Logiin) | Documentation (Laravel) | User Module (Styling & Planning) | User Module
3 | NEHA BHAGAT | Admin Module (Registration) | Admin Module (Registration) | User Module (Logiin) | Database Module (User & Admin Validation ) | User Module (Styling & Planning) | User Module
4 | NIRANJAN SINGH | Admin Module (Registration) | Admin Module (Registration) | User Module (Logiin) | Database Module (User & Admin Validation ) | User Module (Styling & Planning) | User Module
SL NO. | NAME | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
|  | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16 | 2021-12-17 | 2021-12-18
1 | AKSHAY KUMAR | Admin Module (Home Page) | Admin Module (Home Page) | Admin Module (User Roles Control) | Documentation | Laravel Dcumentation | Admin Module (Starred Nav)
2 | KHUSHI | On Leave | User Module (Styling ) | Admin Module (Profile Setting) | User Module (Login Page ) | Laravel Dcumentation | Admin Module (Starred Nav)
3 | NEHA BHAGAT | Admin Module (Home Page) | Admin Module (Home Page) | Admin Module (User Roles Control) | Documentation | laravel frame. | Admin Module (Starred Nav)
4 | NIRANJAN SINGH | Database Module | Admin Module (Home Page) | On Leave | User Module (Login Page ) | On Leave | Admin Module (Starred Nav)
WEEK 4
SL NO. | NAME | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
|  | 2021-12-20 | 2021-12-21 | 2021-12-22 | 2021-12-23 | 2021-12-24 | 2021-12-25
1 | AKSHAY KUMAR | Admin Module (Accessible Rights) | Exam Preparation | Exam Preparation | Internal Exam | Internal Exam | Documentation
2 | KHUSHI | Admin Module (Accessible Rights) | Exam Preparation | Exam Preparation | Internal Exam | Internal Exam | Documentation
3 | NEHA BHAGAT | Admin Module (Accessible Rights) | Exam Preparation | Exam Preparation | Internal Exam | Internal Exam | Documentation
4 | NIRANJAN SINGH | Admin Module (Accessible Rights) | Exam Preparation | Exam Preparation | Internal Exam | Internal Exam | Documentation
WEEK 5
SL NO. | NAME | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
|  | 2021-12-27 | 2021-12-28 | 2021-12-29 | 2021-12-30 | 2021-12-31 | 2021-12-01
1 | AKSHAY KUMAR | User Module (Security) | User Module (Dashboard Styling) | User Module (Security) | User Module (Security) | Leave for Last day of the year | New Year Holiday
2 | KHUSHI | User Module (Security) | User Module (Dashboard Styling) | User Module (Security) | User Module (Security) | Leave for Last day of the year | New Year Holiday
3 | NEHA BHAGAT | User Module (Shared) | User Module (Shared) | Admin Module (Accessible Rights) | User Module (Shared) | Leave for Last day of the year | New Year Holiday
4 | NIRANJAN SINGH | User Module (Shared) | User Module (Shared) | Admin Module (Accessible Rights) | User Module (Shared) | Leave for Last day of the year | New Year Holiday
WEEK 6
SL NO. | NAME | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
|  | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-08
1 | AKSHAY KUMAR | 2022-01-03: PPT preparation; 2022-01-04: PPT preparation
2 | KHUSHI | 2022-01-03: PPT preparation; 2022-01-04: PPT preparation
3 | NEHA BHAGAT | 2022-01-03: PPT preparation; 2022-01-04: PPT preparation
4 | NIRANJAN SINGH | 2022-01-03: PPT preparation; 2022-01-04: PPT preparation
WEEKLY WORK TEMPLATE
KONARK INSTITUTE OF SCIENCE AND TECHNOLOGY
WEEK 1
WEEK 2
WEEK 3